HSIL HACKATHON 2026

7th Edition

TAIWAN HUB

National Taiwan University

College of Public Health  |  Health Economics & AI Lab

MASTER TASK CHECKLIST

| Event Date: | April 10–11, 2026 |
| --- | --- |
| Venue: | NTU College of Public Health |
| Hub Size: | 50–100 participants |
| Winning Teams: | 2 teams advance to global bootcamp |
| Document Date: | February 25, 2026 |

| PHASE 1: SETUP & ADMINISTRATION Completed |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 1 | Confirm Taiwan/NTU hub with HSIL | All |
| 2 | Get NTU listed on HSIL Hackathon landing page | All |
| 3 | Join HSIL Slack workspace | 郭爵安 |
| 4 | Submit NTU logo and organizer info to HSIL | 郭爵安 |
| 5 | Get Airtable access to view and download participant registrations | 郭爵安 |
| 6 | Review all shared materials in Dropbox | 郭爵安 |
| 7 | Confirm weekly meeting schedule with Alem (Wednesday 8:00 PM Taiwan time) | 郭爵安 |

| PHASE 2: FOUNDATIONS February 24 – March 7 |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 8 | Book venue at NTU College of Public Health building – Confirm with CPH administration that event qualifies as free internal booking – Reserve main session room – Update: Made telephone call to confirm price and date: 101 Lecture Hall $79,500 for both 4/10 and 4/11 – Update: Might also need to rent recording cameras to tape the whole event for safety reasons – Update: Reserve after applicant number confirmed, later work | 郭爵安 |

▸ Note: Submit booking request immediately — university room reservations fill quickly.

| 9 | Set the application deadline (Maybe March 31st) – Update: Application deadline scheduled for March 31st | 郭爵安 |
| --- | --- | --- |
| 10 | Adapt HSIL outreach email templates for professors/department heads and also one for individual applicants – Translate key information to Traditional Chinese – Add NTU-specific details and local contact information – Update: Two outreach email templates has been drafted | 陳博士 郭爵安 |
| 11 | Design promotional poster for Taiwan Hub – Use HSIL logo only (never Harvard Chan School logo) – Submit design to Alem for HSIL approval before publishing |  |
| 12 | Set up social media presence – Update: Instagram account created: https://www.instagram.com/hsilhackathon.taiwan/ – Update: Facebook page created: https://www.facebook.com/profile.php?id=61587778492454 | 郭爵安 |
| 13 | Set up official gmail for communication – Update: Official gmail created hsilhackathon.taiwan@gmail.com | 郭爵安 |
| 14 | Publish initial event posts on social media | 郭爵安 |
| 15 | List out potential professors/teacher’s emails for promotion on the event | 郭爵安 |

| PHASE 3: RECRUITMENT March 1 – March 21 |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 13 | Launch advertising campaign — distribute registration link across all channels – University email lists and department bulletin boards – Facebook groups (NTU-related, health and technology communities) – PTT, Dcard, LinkedIn – LINE groups (class groups, student organization groups) |  |
| 14 | Reach out to other NTU departments for cross-disciplinary recruitment – College of Medicine, Engineering, Computer Science, Electrical Engineering, Management – Contact via faculty connections or student associations |  |
| 15 | Contact other Taiwan universities virtually – NTHU, NCKU, NYCU, NTU Hospital, TMU, and others – Email professors or student organization leaders with outreach materials |  |
| 16 | Recruit mentors (target: 6–10 across the following areas) – Healthcare / Clinical – AI / Engineering / Data Science – Public Health / Policy – Design Thinking / UX – Entrepreneurship / Business – Communication / Pitching |  |

▸ Note: Mentors should be available in-person for at least one hour during the hackathon.

| 17 | Recruit judges (3–5 with diverse expertise) – Only required on Day 2 afternoon – Will evaluate final pitches using HSIL-provided judging rubric |  |
| --- | --- | --- |
| 18 | Explore local sponsors for optional local prizes |  |
| 19 | Post weekly social media updates and countdown content – Share success stories from past editions (Vincere Health, Docosan, HERA) – Highlight the innovation pipeline and global bootcamp opportunity |  |

| PHASE 4: PRE-HACKATHON PREPARATION March 21 – April 5 |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 20 | Review applications in Airtable and select participants (target: 50–100) |  |
| 21 | Send confirmation emails to accepted participants – Adapt HSIL confirmation email template for Taiwan |  |
| 22 | Invite all confirmed participants to HSIL Slack workspace |  |
| 23 | Share HSIL Participant Guide with all accepted participants |  |
| 24 | Finalize the 2-day event schedule – Adapt HSIL draft schedule for Taiwan time zone (GMT+8) – Confirm timing for global Zoom welcome session (HSIL will accommodate Asia time zones) |  |
| 25 | Brief mentors using HSIL Mentors Guide and confirm their schedules |  |
| 26 | Brief judges using HSIL Judges Guide and confirm Day 2 afternoon availability |  |
| 27 | Organize optional pre-hackathon online workshops (if time permits) – Design Thinking workshop – AI and technology fundamentals – Business model development and pitching skills |  |
| 28 | Test AV equipment and Zoom connection at the venue |  |
| 29 | Prepare event logistics – Name badges for participants, mentors, and judges – Signage and directional signs at venue – Print schedules, judging rubrics, and team formation materials – Swag and T-shirts (submit designs to HSIL for approval first) |  |
| 30 | Arrange catering and food for both days – Day 1: lunch, snacks, and beverages – Day 2: lunch, snacks, beverages, and celebration refreshments |  |

| PHASE 5: HACKATHON DAY 1 April 10 (Friday) |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 31 | Set up venue: signage, registration desk, AV system, breakout rooms |  |
| 32 | Registration and check-in of participants |  |
| 33 | Opening ceremony — NTU welcome remarks |  |
| 34 | Global HSIL welcome session via Zoom from Harvard |  |
| 35 | Play HSIL recorded keynote panel: AI for Health Systems |  |
| 36 | Hack 101 — explain rules, judging criteria, timeline, and Q&A |  |
| 37 | Team formation session for individuals without pre-formed teams |  |
| 38 | Hacking begins with mentoring sessions throughout the day – Rotate mentors across teams in one-hour blocks – Health/Clinical, Technology/AI, and Impact/Business mentoring tracks |  |
| 39 | End of day: draw randomized presentation order for Day 2 |  |

| PHASE 6: HACKATHON DAY 2 April 11 (Saturday) |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 40 | Play HSIL recorded keynote: Empowering Women in HealthTech |  |
| 41 | Focused mentoring and pitch practice sessions |  |
| 42 | Final pitching: 3 minutes per team plus 2 minutes Q&A from judges |  |
| 43 | Judge deliberation (judges convene privately to score and decide) |  |
| 44 | Award ceremony: announce 2 winning teams – Winners advance to HSIL global 2-week bootcamp – Award local prizes if sponsors have been secured |  |
| 45 | Closing remarks — explain next steps for winning teams |  |
| 46 | Capture event photos and group photos for social media |  |

| PHASE 7: POST-HACKATHON April 12 onwards |  |  |
| --- | --- | --- |
| # | Task | Person Responsible |
| 47 | Submit winning team details to HSIL for the global bootcamp – Pipeline: 2-week bootcamp → top 20 extended bootcamp → 8 teams VIP → Demo Day with VCs |  |
| 48 | Post event photos and highlights on social media – Tag @Harvard Health Systems Innovation Lab (LinkedIn) – Tag @Harvardhsi (Instagram) |  |
| 49 | Send thank-you messages to participants, mentors, judges, and sponsors |  |
| 50 | Complete any post-event reporting required by HSIL |  |
| 51 | Support winning teams as they enter the bootcamp pipeline |  |
| 52 | Consider local recognition for additional standout teams |  |

KEY CONTACTS & RESOURCES

| HSIL Hackathon Email | hsilhackathon@hsph.harvard.edu |
| --- | --- |
| Communications Approval | Alem Aminu Osman (alemosman@hsph.harvard.edu) |
| Registration Link | https://airtable.com/app06PiI7r4PVqBdt/pagFJFqJW3xFqnRFw/form |
| Faculty Advisor | 李達宇教授 (Professor John Tayu Lee), 620 Lab, NTU CPH |
| Social Media Tags | @Harvard Health Systems Innovation Lab (LinkedIn), @Harvardhsi (Instagram) |

IMPORTANT REMINDERS

1.  Always attribute the hackathon to “Health Systems Innovation Lab” — never state that Harvard organized the event.

2.  Only use the HSIL logo on all materials. The Harvard Chan School logo must never be used.

3.  Submit ALL promotional and merchandise designs to HSIL for approval before production or distribution.

4.  No coding or working prototype is required from participants — concept-stage ideas are welcome.

5.  Teams may address any health system + AI topic. The 11 priority health challenges are optional guidance.

6.  Recommended team size is 3–5 members. Individuals may register and will be matched with a team.